## Dashboard
SD GROUP - EMPLOYEE HANDBOOK REGISTER
SPACEDRAFT - GOVERNANCE DASHBOARD
All figures are live formulas reading the Register tab.
GOVERNANCE SUMMARY
Metric | Value
Total books
Books requiring HR review
Books requiring legal review (legal-sensitive)
Books requiring management approval
Books requiring employee acknowledgement
Books requiring quiz / assessment
PRODUCTION STATUS
Status | Books
Not Started
Draft Content Created
HR Review Pending
HR Approved
Legal Review Pending
Legal Approved
Management Review Pending
Management Approved
PDF Designed
PDF Final Checked
Uploaded to SD Academy
Access Tagged
Acknowledgement Campaign Live
Employee Acknowledgement Completed
Archived / Superseded
ACCESS LEVEL SPREAD
Access band | Books
L1-L5
L2-L5
L3-L5
L4-L5
L5
WEBSITE UPLOAD PROGRESS
Upload step | Done
1. File Uploaded
2. Folder Path Verified
3. Access Tags Applied
4. Course Linked
5. Quiz Attached
6. Live Link Tested
7. Ack Campaign Pushed
BOOKS BY CATEGORY
Category | Books
Company / Division Handbook
Department Handbook
Leadership Handbook
Management Handbook
SOP Handbook

## Register
SD GROUP - EMPLOYEE HANDBOOK REGISTER
SPACEDRAFT - HANDBOOK REGISTER (28 books)
Standalone company register. Source of truth for this entity. Update Current Status here; the Dashboard recalculates automatically.
Book ID | Book Title | Brand / Division | Department | Book Category | Employee Level Access | Confidentiality Level | Book Owner | HR Review Required | Legal Review Required | Management Approval Required | Employee Acknowledgement Required | Quiz / Assessment Required | Passing Score | Related SD Academy Course ID | SD Academy Folder Path | PDF File Name | Version Number | Current Status | Priority | Production Wave | Review Frequency | Next Review Due Date | Remarks / Gap Notes
SD-BRD-01 | SpaceDraft Company Handbook | All Divisions | Company-wide | Company / Division Handbook | L1-L5 | Internal | HRBP - SpaceDraft India Pvt Ltd | Yes | Yes | Yes | Yes | No | - | SDA-CRS-SD-BRD-01 | SD Academy/02_SpaceDraft/01_Company_Handbooks | SDG_SpaceDraft_Company_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | High | Wave 2 | Annual + on law change | 2027-04-01 | Company and brand handbook combined (single-brand entity)
SD-DPT-01 | CRM Department Handbook | SpaceDraft | CRM | Department Handbook | L1-L5 | Internal | Dept Head - SD/CRM | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-01 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_CRM_Department_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | High | Wave 3 | Annual | 2027-04-01
SD-DPT-02 | Business Development Handbook | SpaceDraft | Business Development | Department Handbook | L1-L5 | Internal | Dept Head - SD/Business Development | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-02 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Business_Development_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | High | Wave 3 | Annual | 2027-04-01
SD-DPT-03 | Design Studio Handbook | SpaceDraft | Design Studio | Department Handbook | L1-L5 | Internal | Dept Head - SD/Design Studio | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-03 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Design_Studio_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | High | Wave 3 | Annual | 2027-04-01
SD-DPT-04 | Tender Department Handbook | SpaceDraft | Tender | Department Handbook | L2-L5 | Internal | Dept Head - SD/Tender | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-04 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Tender_Department_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | High | Wave 3 | Annual | 2027-04-01
SD-DPT-05 | Quantity Survey Handbook | SpaceDraft | Quantity Survey | Department Handbook | L2-L5 | Internal | Dept Head - SD/Quantity Survey | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-05 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Quantity_Survey_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual | 2027-04-01
SD-DPT-06 | Procurement Handbook | SpaceDraft | Procurement | Department Handbook | L1-L5 | Internal | Dept Head - SD/Procurement | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-06 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Procurement_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual | 2027-04-01
SD-DPT-07 | Project Management Handbook | SpaceDraft | Project Management | Department Handbook | L1-L5 | Internal | Dept Head - SD/Project Management | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-07 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Project_Management_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual | 2027-04-01
SD-DPT-08 | Project Execution Handbook | SpaceDraft | Project Execution | Department Handbook | L1-L5 | Internal | Dept Head - SD/Project Execution | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-08 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Project_Execution_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual | 2027-04-01
SD-DPT-09 | EHS Department Handbook | SpaceDraft | EHS | Department Handbook | L1-L5 | Internal | Dept Head - SD/EHS | Yes | Yes | Yes | Yes | Yes | 80 | SDA-CRS-SD-DPT-09 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_EHS_Department_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual + on law change | 2027-04-01
SD-DPT-10 | Quality Assurance Handbook | SpaceDraft | Quality Assurance | Department Handbook | L1-L5 | Internal | Dept Head - SD/Quality Assurance | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-10 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Quality_Assurance_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual | 2027-04-01
SD-DPT-11 | Facility Management Handbook | SpaceDraft | Facility Management | Department Handbook | L1-L5 | Internal | Dept Head - SD/Facility Management | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-11 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Facility_Management_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual | 2027-04-01
SD-SOP-01 | QA/QC Checklist & Inspection Handbook | SpaceDraft | Quality | SOP Handbook | L2-L5 | Internal | Dept Head - SD/Quality | Yes | No | Yes | No | No | - | SDA-CRS-SD-SOP-01 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_QA_QC_Checklist_Inspection_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Half-yearly | 2027-01-01 | ITP formats and stage inspections
SD-SOP-02 | Client Handover, DLP & Warranty Handbook | SpaceDraft | Projects | SOP Handbook | L2-L5 | Internal | Dept Head - SD/Projects | Yes | Yes | Yes | No | No | - | SDA-CRS-SD-SOP-02 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_Client_Handover_DLP_Warranty_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual + on law change | 2027-04-01 | Defect liability and warranty obligations
SD-SOP-03 | Material Reconciliation Handbook | SpaceDraft | Stores / QS | SOP Handbook | L2-L5 | Internal | Dept Head - SD/Stores / QS | Yes | No | Yes | No | No | - | SDA-CRS-SD-SOP-03 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_Material_Reconciliation_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Half-yearly | 2027-01-01
SD-SOP-04 | Subcontractor Management Handbook | SpaceDraft | Projects | SOP Handbook | L3-L5 | Internal | Dept Head - SD/Projects | Yes | Yes | Yes | No | No | - | SDA-CRS-SD-SOP-04 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_Subcontractor_Management_Handbook_L3-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual + on law change | 2027-04-01 | CLRA compliance and WO discipline
SD-SOP-05 | Permit-to-Work & Site Safety Procedure Handbook | SpaceDraft | EHS | SOP Handbook | L1-L5 | Internal | Dept Head - SD/EHS | Yes | Yes | Yes | No | Yes | 80 | SDA-CRS-SD-SOP-05 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_Permit_to_Work_Site_Safety_Procedure_Handbook_L1-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual + on law change | 2027-04-01 | Hot work / height / confined space PTW
SD-SOP-06 | Measurement & Billing Handbook | SpaceDraft | QS | SOP Handbook | L2-L5 | Internal | Dept Head - SD/QS | Yes | Yes | Yes | No | No | - | SDA-CRS-SD-SOP-06 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_Measurement_Billing_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Annual + on law change | 2027-04-01 | Client RA bills and subcontractor billing
SD-SOP-07 | Project Closure & Documentation Handbook | SpaceDraft | Projects | SOP Handbook | L3-L5 | Internal | Dept Head - SD/Projects | Yes | No | Yes | No | No | - | SDA-CRS-SD-SOP-07 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_Project_Closure_Documentation_Handbook_L3-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Half-yearly | 2027-01-01
SD-SOP-08 | Site Mobilisation & Demobilisation Handbook | SpaceDraft | Projects | SOP Handbook | L2-L5 | Internal | Dept Head - SD/Projects | Yes | No | Yes | No | No | - | SDA-CRS-SD-SOP-08 | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDG_SpaceDraft_Site_Mobilisation_Demobilisation_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 4 | Half-yearly | 2027-01-01
SD-DPT-12 | Legal & Compliance Handbook | SpaceDraft | Legal & Compliance | Department Handbook | L3-L5 | Internal | Dept Head - SD/Legal & Compliance | Yes | Yes | Yes | Yes | No | - | SDA-CRS-SD-DPT-12 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Legal_Compliance_Handbook_L3-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 5 | Annual + on law change | 2027-04-01
SD-DPT-13 | Accounts Handbook | SpaceDraft | Accounts | Department Handbook | L2-L5 | Internal | Dept Head - SD/Accounts | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-13 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Accounts_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 5 | Annual | 2027-04-01
SD-DPT-14 | Finance Handbook | SpaceDraft | Finance | Department Handbook | L2-L5 | Internal | Dept Head - SD/Finance | Yes | Yes | Yes | Yes | No | - | SDA-CRS-SD-DPT-14 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Finance_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 5 | Annual + on law change | 2027-04-01
SD-DPT-15 | HR Handbook | SpaceDraft | HR | Department Handbook | L2-L5 | Internal | Dept Head - SD/HR | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-15 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_HR_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 5 | Annual | 2027-04-01
SD-DPT-16 | Admin Handbook | SpaceDraft | Admin | Department Handbook | L2-L5 | Internal | Dept Head - SD/Admin | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-16 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_Admin_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 5 | Annual | 2027-04-01
SD-DPT-17 | IT Handbook | SpaceDraft | IT | Department Handbook | L2-L5 | Internal | Dept Head - SD/IT | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-DPT-17 | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDG_SpaceDraft_IT_Handbook_L2-L5_V1.0.pdf | 1 | PDF Final Checked | Medium | Wave 5 | Annual | 2027-04-01
SD-LDR-01 | SpaceDraft Leadership Handbook | SpaceDraft | Leadership | Leadership Handbook | L4-L5 | Restricted | Brand Head - SpaceDraft | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-LDR-01 | SD Academy/02_SpaceDraft/06_Management_Handbooks | SDG_SpaceDraft_Leadership_Handbook_L4-L5_V1.0.pdf | 1 | PDF Final Checked | High | Wave 6 | Annual | 2027-04-01
SD-MGT-01 | SpaceDraft Management Handbook | SpaceDraft | Management | Management Handbook | L4-L5 | Restricted | Brand Head - SpaceDraft | Yes | No | Yes | Yes | No | - | SDA-CRS-SD-MGT-01 | SD Academy/02_SpaceDraft/06_Management_Handbooks | SDG_SpaceDraft_Management_Handbook_L4-L5_V1.0.pdf | 1 | PDF Final Checked | High | Wave 6 | Annual | 2027-04-01 | Was Management Handbook

## Level_Matrix
SD GROUP - EMPLOYEE HANDBOOK REGISTER
SPACEDRAFT - LEVEL MATRIX (L1-L5)
Cumulative: each level includes every level below it. Yes = the book sits in that level's path for people in scope.
Book ID | Book Title | Brand / Division | Department | Book Category | Access Band | Min Level | L1 | L2 | L3 | L4 | L5
SD-BRD-01 | SpaceDraft Company Handbook | All Divisions | Company-wide | Company / Division Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-01 | CRM Department Handbook | SpaceDraft | CRM | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-02 | Business Development Handbook | SpaceDraft | Business Development | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-03 | Design Studio Handbook | SpaceDraft | Design Studio | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-06 | Procurement Handbook | SpaceDraft | Procurement | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-07 | Project Management Handbook | SpaceDraft | Project Management | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-08 | Project Execution Handbook | SpaceDraft | Project Execution | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-09 | EHS Department Handbook | SpaceDraft | EHS | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-10 | Quality Assurance Handbook | SpaceDraft | Quality Assurance | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-11 | Facility Management Handbook | SpaceDraft | Facility Management | Department Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-SOP-05 | Permit-to-Work & Site Safety Procedure Handbook | SpaceDraft | EHS | SOP Handbook | L1-L5 | L1 | Yes | Yes | Yes | Yes | Yes
SD-DPT-04 | Tender Department Handbook | SpaceDraft | Tender | Department Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-DPT-05 | Quantity Survey Handbook | SpaceDraft | Quantity Survey | Department Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-DPT-13 | Accounts Handbook | SpaceDraft | Accounts | Department Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-DPT-14 | Finance Handbook | SpaceDraft | Finance | Department Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-DPT-15 | HR Handbook | SpaceDraft | HR | Department Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-DPT-16 | Admin Handbook | SpaceDraft | Admin | Department Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-DPT-17 | IT Handbook | SpaceDraft | IT | Department Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-SOP-01 | QA/QC Checklist & Inspection Handbook | SpaceDraft | Quality | SOP Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-SOP-02 | Client Handover, DLP & Warranty Handbook | SpaceDraft | Projects | SOP Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-SOP-03 | Material Reconciliation Handbook | SpaceDraft | Stores / QS | SOP Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-SOP-06 | Measurement & Billing Handbook | SpaceDraft | QS | SOP Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-SOP-08 | Site Mobilisation & Demobilisation Handbook | SpaceDraft | Projects | SOP Handbook | L2-L5 | L2 | - | Yes | Yes | Yes | Yes
SD-DPT-12 | Legal & Compliance Handbook | SpaceDraft | Legal & Compliance | Department Handbook | L3-L5 | L3 | - | - | Yes | Yes | Yes
SD-SOP-04 | Subcontractor Management Handbook | SpaceDraft | Projects | SOP Handbook | L3-L5 | L3 | - | - | Yes | Yes | Yes
SD-SOP-07 | Project Closure & Documentation Handbook | SpaceDraft | Projects | SOP Handbook | L3-L5 | L3 | - | - | Yes | Yes | Yes
SD-LDR-01 | SpaceDraft Leadership Handbook | SpaceDraft | Leadership | Leadership Handbook | L4-L5 | L4 | - | - | - | Yes | Yes
SD-MGT-01 | SpaceDraft Management Handbook | SpaceDraft | Management | Management Handbook | L4-L5 | L4 | - | - | - | Yes | Yes

## Level_Guide
SD GROUP - EMPLOYEE HANDBOOK REGISTER
5-LEVEL LEARNING STRUCTURE
Levels define who reads what. Paths are cumulative.
Level | Level Name | Typical Roles | What This Level Adds | Completion Gate | SpaceDraft books at this level
L1 | L1 - Foundation | Trainee / Executive / Operator | Group core conduct & safety, own company handbook, own department basics | Induction: complete within 30 days of joining | 11
L2 | L2 - Practitioner | Senior Executive / Technician / Specialist | Adds own-function SOPs: how the job is done to standard | Complete before independent working / unsupervised sign-off | 23
L3 | L3 - Senior / Coordinator | Senior Specialist / Team Coordinator / Lead | Adds compliance books, escalation ownership, audit-facing material | Complete before holding escalation or client-facing authority | 26
L4 | L4 - Manager / HOD | Manager / Head of Department | Adds the management set: DoA, MIS review, appraisal, risk, targets, HOD role | Complete before confirmation in a people-management role | 28
L5 | L5 - Leadership | Company Head / Function Head / Management | Adds leadership set: Leadership Operating and Strategic Planning & Review | Complete within 90 days of appointment to leadership | 28

## Upload_Checklist
SD GROUP - EMPLOYEE HANDBOOK REGISTER
SPACEDRAFT - SD ACADEMY WEBSITE UPLOAD CHECKLIST (28 books)
Portal admin working sheet. Complete every tick column per book, then set Current Status in the Register to 'Uploaded to SD Academy' / 'Access Tagged'.
A. PRE-UPLOAD STANDARDS - verify these before uploading any file
1. File is the FINAL branded PDF - entity logo on cover, corner logo and watermark on every interior page.
2. File name matches the 'PDF File Name' column EXACTLY (case, underscores and _V1.0.pdf suffix included).
3. Version block reads V1.0 ¦ Effective 03-Jul-2026 ¦ Next Review 01-Jul-2027 on the document control page.
4. Upload to the exact 'SD Academy Folder Path' shown - do not create new folders or rename existing ones.
5. Link the file to its 'Related SD Academy Course ID' before publishing.
6. Apply access tags exactly as the 'Access Tag' column states (company / division / level).
7. Where Quiz = Yes, attach the mapped quiz and set the pass mark to 80% before the book goes live.
8. Where Legal Review = Yes, confirm legal sign-off is recorded in the Register BEFORE upload.
9. After publishing, open the live link as a test user at the lowest permitted level and confirm it renders.
10. Only then push the acknowledgement campaign (7-day completion window).
B. PER-BOOK UPLOAD CHECKLIST
# | Book ID | PDF File Name (exact) | SD Academy Folder Path | Course ID | Access Tag (company ¦ division ¦ level) | Quiz | Ack | Legal Sign-off Confirmed | 1. File Uploaded | 2. Folder Path Verified | 3. Access Tags Applied | 4. Course Linked | 5. Quiz Attached | 6. Live Link Tested | 7. Ack Campaign Pushed | Uploaded By | Upload Date | Notes / Issues
1 | SD-BRD-01 | SDG_SpaceDraft_Company_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/01_Company_Handbooks | SDA-CRS-SD-BRD-01 | SpaceDraft ¦ All Divisions ¦ L1-L5 | No | Yes | REQUIRED |  |  |  |  | n/a
2 | SD-DPT-01 | SDG_SpaceDraft_CRM_Department_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-01 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
3 | SD-DPT-02 | SDG_SpaceDraft_Business_Development_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-02 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
4 | SD-DPT-03 | SDG_SpaceDraft_Design_Studio_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-03 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
5 | SD-DPT-04 | SDG_SpaceDraft_Tender_Department_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-04 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | Yes | n/a |  |  |  |  | n/a
6 | SD-DPT-05 | SDG_SpaceDraft_Quantity_Survey_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-05 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | Yes | n/a |  |  |  |  | n/a
7 | SD-DPT-06 | SDG_SpaceDraft_Procurement_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-06 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
8 | SD-DPT-07 | SDG_SpaceDraft_Project_Management_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-07 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
9 | SD-DPT-08 | SDG_SpaceDraft_Project_Execution_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-08 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
10 | SD-DPT-09 | SDG_SpaceDraft_EHS_Department_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-09 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | Yes | Yes | REQUIRED
11 | SD-DPT-10 | SDG_SpaceDraft_Quality_Assurance_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-10 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
12 | SD-DPT-11 | SDG_SpaceDraft_Facility_Management_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-11 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | No | Yes | n/a |  |  |  |  | n/a
13 | SD-SOP-01 | SDG_SpaceDraft_QA_QC_Checklist_Inspection_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-01 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | No | n/a |  |  |  |  | n/a
14 | SD-SOP-02 | SDG_SpaceDraft_Client_Handover_DLP_Warranty_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-02 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | No | REQUIRED |  |  |  |  | n/a
15 | SD-SOP-03 | SDG_SpaceDraft_Material_Reconciliation_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-03 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | No | n/a |  |  |  |  | n/a
16 | SD-SOP-04 | SDG_SpaceDraft_Subcontractor_Management_Handbook_L3-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-04 | SpaceDraft ¦ SpaceDraft ¦ L3-L5 | No | No | REQUIRED |  |  |  |  | n/a
17 | SD-SOP-05 | SDG_SpaceDraft_Permit_to_Work_Site_Safety_Procedure_Handbook_L1-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-05 | SpaceDraft ¦ SpaceDraft ¦ L1-L5 | Yes | No | REQUIRED
18 | SD-SOP-06 | SDG_SpaceDraft_Measurement_Billing_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-06 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | No | REQUIRED |  |  |  |  | n/a
19 | SD-SOP-07 | SDG_SpaceDraft_Project_Closure_Documentation_Handbook_L3-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-07 | SpaceDraft ¦ SpaceDraft ¦ L3-L5 | No | No | n/a |  |  |  |  | n/a
20 | SD-SOP-08 | SDG_SpaceDraft_Site_Mobilisation_Demobilisation_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/04_SOP_Handbooks | SDA-CRS-SD-SOP-08 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | No | n/a |  |  |  |  | n/a
21 | SD-DPT-12 | SDG_SpaceDraft_Legal_Compliance_Handbook_L3-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-12 | SpaceDraft ¦ SpaceDraft ¦ L3-L5 | No | Yes | REQUIRED |  |  |  |  | n/a
22 | SD-DPT-13 | SDG_SpaceDraft_Accounts_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-13 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | Yes | n/a |  |  |  |  | n/a
23 | SD-DPT-14 | SDG_SpaceDraft_Finance_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-14 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | Yes | REQUIRED |  |  |  |  | n/a
24 | SD-DPT-15 | SDG_SpaceDraft_HR_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-15 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | Yes | n/a |  |  |  |  | n/a
25 | SD-DPT-16 | SDG_SpaceDraft_Admin_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-16 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | Yes | n/a |  |  |  |  | n/a
26 | SD-DPT-17 | SDG_SpaceDraft_IT_Handbook_L2-L5_V1.0.pdf | SD Academy/02_SpaceDraft/03_Department_Handbooks | SDA-CRS-SD-DPT-17 | SpaceDraft ¦ SpaceDraft ¦ L2-L5 | No | Yes | n/a |  |  |  |  | n/a
27 | SD-LDR-01 | SDG_SpaceDraft_Leadership_Handbook_L4-L5_V1.0.pdf | SD Academy/02_SpaceDraft/06_Management_Handbooks | SDA-CRS-SD-LDR-01 | SpaceDraft ¦ SpaceDraft ¦ L4-L5 | No | Yes | n/a |  |  |  |  | n/a
28 | SD-MGT-01 | SDG_SpaceDraft_Management_Handbook_L4-L5_V1.0.pdf | SD Academy/02_SpaceDraft/06_Management_Handbooks | SDA-CRS-SD-MGT-01 | SpaceDraft ¦ SpaceDraft ¦ L4-L5 | No | Yes | n/a |  |  |  |  | n/a
C. SIGN-OFF
Role | Name | Signature / Digital Confirmation | Date
Portal Admin (upload complete)
Group HR (access tags verified)
Company Head (release approved)

## Access_Matrix
SD GROUP - EMPLOYEE HANDBOOK REGISTER
ACCESS BAND REFERENCE
What each access band is used for across SD Group.
Access band | Used for
L1-L5 | Common employee, code of conduct, attendance & leave, HR basics, company/division handbook, department execution, basic safety, basic training, acknowledgement books
L2-L5 | SOP-heavy, tool usage, department workflow, execution process, software books
L3-L5 | Senior coordination, client escalation, advanced reporting, commercial process, data quality, compliance process
L4-L5 | Management review, approval matrix, team monitoring, internal audit, escalation control, corrective action
L5 | Founder/director strategy, confidential strategy, restructuring, sensitive legal strategy, high-level governance

## Status_Flow
SD GROUP - EMPLOYEE HANDBOOK REGISTER
STATUS FLOW - 15 STAGES
Each book moves through these stages. Use the dropdown in Register.
# | Stage | Gate owner | Exit criteria
1 | Not Started | Register owner | Data sheet received
2 | Draft Content Created | Book Owner | Full draft on approved template
3 | HR Review Pending | Group HR | Queued for HR check
4 | HR Approved | Group HR | Policy consistency verified
5 | Legal Review Pending | Legal & Compliance | Queued where Legal = Yes
6 | Legal Approved | Legal & Compliance | Statutory sign-off recorded
7 | Management Review Pending | Brand Head / CHRO | Queued for approval
8 | Management Approved | Brand Head / CHRO | Signed approval in register
9 | PDF Designed | Design cell | Branded PDF with footer + metadata
10 | PDF Final Checked | QC reviewer | Proof-read; version block verified
11 | Uploaded to SD Academy | Portal admin | Live in correct folder path
12 | Access Tagged | Portal admin | Company/division/level/role tags applied
13 | Acknowledgement Campaign Live | Portal admin | Ack task pushed to target employees
14 | Employee Acknowledgement Completed | Group HR | >= 95% acknowledged; laggards escalated
15 | Archived / Superseded | Portal admin | Old version moved to 12_Archived_Versions

## Change_Log
SD GROUP - EMPLOYEE HANDBOOK REGISTER
CHANGE LOG
Record every structural or status change to this register.
Date | Version | Change Type | Description | By
23-Jul-2026 | v1.0 | Register split from group master - SpaceDraft | SpaceDraft register separated from SDG_Handbook_Master_Register_v3.1 into a standalone workbook covering 28 books. All 28 handbooks produced as entity-branded, QC-audited PDFs; status 'PDF Final Checked'. Next stages: HR/Legal/Management sign-off, SD Academy upload, access tagging, acknowledgement campaign. | Group HR

## Lists (hidden)
Validation lists (do not delete)
Status | Access | Yes/No
Not Started | L1-L5 | Yes
Draft Content Created | L2-L5 | No
HR Review Pending | L3-L5
HR Approved | L4-L5
Legal Review Pending | L5
Legal Approved
Management Review Pending
Management Approved
PDF Designed
PDF Final Checked
Uploaded to SD Academy
Access Tagged
Acknowledgement Campaign Live
Employee Acknowledgement Completed
Archived / Superseded